## Read me
Website migration URL-mapping template
Version 1.0, published October 5, 2026. Guide: https://guides.shoutex.com/website-platforms/website-migration-seo-checklist/
How to use: 1) Paste every old URL from a crawl, your sitemap, Search Console and analytics into column A of 'URL map'. 2) Add clicks and backlinks. 3) Choose an action and a new URL for every row. 4) After launch, record the final status in column M.
Priority is calculated from clicks and backlinks (High, Medium, Low). Check every High row by hand on launch day.
Google advises keeping redirects for as long as possible, generally at least one year (Google Search Central, Site moves with URL changes).
The four example rows use a fictional site. Delete them before you start.
Published by ShoutEx (https://guides.shoutex.com/website-platforms/). Free to use and share; please link to the guide when you cite it.
Legend: orange cells with blue text are inputs you can edit. Black text is a formula or a fixed label.

## URL map
Old URL | Status code | Page type | Clicks (last 90 days) | Backlinks (referring domains) | Priority | Action (keep / redirect / merge / remove) | New URL | Redirect type | Title and meta carried over? | Canonical updated? | Internal links updated? | Tested after launch (final status) | Notes
/blog/12-route-planning-guide | 200 | Post | 1840 | 14 | High | redirect | /blog/route-planning-guide/ | 301 | yes | yes | yes |  | Top page; check by hand
/pricing.html | 200 | Page | 960 | 3 | High | redirect | /pricing/ | 301 | yes | yes | yes
/features/dispatch | 200 | Page | 310 | 2 | High | merge | /product/ | 301 | yes | yes | yes |  | Content merged into Product
/old-webinar-2023 | 200 | Landing page | 4 | 0 | Low | remove |  | 410 | n/a | n/a | n/a |  | No traffic, no links

## Launch checks
Phase | Check | Done? | Notes
Before | Crawl the old site and export every URL
Before | Export pages with clicks and impressions from Search Console
Before | List pages with backlinks
Before | Choose an action and new URL for every row
Before | Copy titles, descriptions and key content to new pages
Before | Benchmark clicks, rankings and conversions for top pages
Launch | Every mapped URL returns one 301 to the right page, then 200; no chains
Launch | No noindex or password protection left from staging
Launch | robots.txt allows crawling
Launch | Canonical tags point to new URLs
Launch | New XML sitemap submitted in Search Console
Launch | Analytics, tag manager and conversion events fire
After | Week 1: fix 404s and redirect errors
After | Weeks 1-2: confirm top 50 new URLs are indexed
After | Weeks 2-6: compare clicks on top pages with the benchmark
After | Weeks 4-12: review conversions by landing page
After | Keep redirects for at least one year